## Slide 1
LEHMAN ROAD RECONSTRUCTION
CITY COUNCIL
PROJECT STATUS UPDATE
OCTOBER 8, 2014

## Slide 2
01
Proposed Typical Sections
02
Right of Way and Utility Impacts
03
Budget and Cost Estimate Update
04
Schedule of Activities

## Slide 3
01
Proposed Typical Sections

## Slide 4: PROPOSED TYPICAL SECTIONS
Functional Classification: Minor Collector
ADT (2014): 4114 VPD (2034): 7430 VPD 4.6% Heavy Vehicles
Existing Lehman Road Typical Section
Alternate 1 – Proposed Typical Section
  As presented during bond election.
  Four Lane sections on either end of project with a narrower 3 lane section through the subdivisions.

## Slide 5: PROPOSED TYPICAL SECTIONSALTERNATE 1 (CON’T)
LAKE KYLE PARK
CONC BOX CULVERTS
FOUR SEASONS FARMS
PRAIRIE ON THE CREEK

## Slide 6: PROPOSED TYPICAL SECTIONSALTERNATE 1 (CON’T)
PRAIRIE ON THE CREEK
STEEPLECHASE
FOUR SEASONS FARMS
BRIDGE

## Slide 7: PROPOSED TYPICAL SECTIONS ALTERNATE 1 (CON’T)
Three lane section maintained to just south of intersection with Goforth Road. A fourth lane added to provide for dedicated left and right turn lanes at the intersection
Signal warrant study being preformed for the Lehman Road / Goforth intersection
Corner clip of parcel in southwest corner of intersection to provide improved sight distance
STEEPLECHASE
LEHMAN HIGH SCHOOL

## Slide 8: PROPOSED TYPICAL SECTIONS
Existing Lehman Road Typical Section
Alternate 2 – Proposed Typical Section
  Maintain functionality
  Maintain 3 lane section throughout
  Dedicated left and right turn lanes at FM 150

## Slide 9: PROPOSED TYPICAL SECTIONSALTERNATE 2 (CON’T)
Maintain functionality
Maintain 3 lane section throughout
Narrower non-multiuse travel lanes

## Slide 10: PROPOSED TYPICAL SECTIONS ALTERNATE 2 (CON’T)
Three lane section maintained to just south of intersection with Goforth Road. A fourth lane added to provide for dedicated left and right turn lanes at the intersection
Same as Alternate 1 but with 11’ lanes.
Signal warrant study being preformed for the Lehman Road / Goforth intersection
Corner clip of parcel in southwest corner of intersection to provide improved sight distance
LEHMAN HIGH SCHOOL

## Slide 11: PROPOSED TYPICAL SECTIONSALTERNATE 2A
Minimize section in areas within floodplain that are not reasonably developable.
Tributary to Plum Creek (Stream Plum-1) & Plum Creek.
Estimated $600,000 project savings.
End 3-Ln Section
Begin 2-Ln Section
End 2-Ln Section
Begin 3-Ln Section
3 Lane section
2 Lane Section
End 3-Ln Section
Begin 2-Ln Section
End 2-Ln Section
Begin 3-Ln Section
2-Ln Bridge
2-Ln Bridge

## Slide 12: PROPOSED TYPICAL SECTIONS
Existing Lehman Road Typical Section
Alternate 3 – Proposed Typical Section
  Maintain functionality
  Minimize pavement by utilizing 2 lane section to maximum extent
  2 lane bridge over stream Plum-1 (SCS Dam) & Plum Creek
  Dedicated left and right turn lanes at FM 150 on south end of project.
3 Lane section
2 Lane Section

## Slide 13: PROPOSED TYPICAL SECTIONSALTERNATE 3 (CON’T)
Dedicated left turn lanes at intersections only
  Masonwood Drive, Primrose Blvd., Goldenrod St. and Hiver St.
MASONWOOD DR.
3 Lane section
2 Lane Section
PRIMROSE BLVD
GOLDENROD ST
HIVER ST
HALLIE DRIVE

## Slide 14: PROPOSED TYPICAL SECTIONSALTERNATE 3 (CON’T)
4 Lane section
3 Lane section
2 Lane Section
Dedicated left turn lanes at Brutus Drive
Dedicated left turn lane into Lehman HS
Dedicated left and right turn lanes onto Goforth Road
BRUTUS DR
GOFORTH RD
LEHMAN HIGH SCHOOL

## Slide 15: PROPOSED TYPICAL SECTIONSProposed Pavement Section
Geotechnical Engineer provided 4 options
Option 3 presented below:
  18-yr design life
  Periodic maintenance will be required
    Crack seal (as necessary)
    Periodic Overlay (6 – 8 yrs)
  Proposed Pavement Section
    4” of Type C HMAC
    10” of Flexible Base Material
    Geogrid (Ty II)
    8” of Lime Stabilized Subgrade
  Geotechnical Consultant finalizing investigation for sulfates in soils. If sulfates are found, double lime treatment or other chemical measures will be required to control impacts on pavement structure.

## Slide 16
02
Right of Way and Utility Impacts

## Slide 17: ROW IMPACTS
ALTERNATE 1
Total of 29 Parcels impacted
Small ROW take of 5’ required from back yards of about 15 homes in the Four Season Farms subdivision.
  Total ROW Acquisition ~ 1.73 Acres (23 Parcels)
Easements are slope easements. Property is retained by owner, but use and future development is limited by the slope easement.
  Approximately 60’ each side @ Stream Plum-1 (Lake Kyle Park)
  Approximately 30’ each side @ Plum Creek crossing
  Total Slope Easement Required ~ 3.51 Acres (6 Parcels)
** City of Kyle Property

## Slide 18: ROW IMPACTS
ALTERNATE 2
Total of 13 parcels impacted
NO ROW take required from back yards of homes in the Four Seasons Farms subdivision.
  Total ROW Acquisition ~ 1.03 Acres (6 Parcels)
Easements are slope easements. Property is retained by owner, but use and future development is limited by the slope easement.
  Approximately 60’ each side @ Stream Plum-1 (Lake Kyle Park)
  Approximately 30’ each side @ Plum Creek crossing
  Total Slope Easement Required ~ 3.69 Acres (7 Parcels)
Slope easement acreage slightly decreased for Alternate 2 +2A. Decrease from 3.69 acres to 2.75 acres.
  Approximately 45’ each side @ Stream Plum-1 (Lake Kyle Park)
  Approximately 15’ each side @ Plum Creek crossing
** City of Kyle Property

## Slide 19: ROW IMPACTS
ALTERNATE 3
Total of 13 parcels impacted
NO ROW take required from back yards of homes in the Prairie on the Creek subdivision.
  Total ROW Acquisition ~ 0.91 Acres (6 Parcels)
Easements are slope easements. Property is retained by owner, but use and future development is limited by the slope easement.
  Approximately 45’ each side @ Stream Plum-1 (Lake Kyle Park)
  Approximately 15’ each side @ Plum Creek crossing
  Total Slope Easement Required ~ 2.75 Acres (7 Parcels)
** City of Kyle Property

## Slide 20: UTILITY IMPACTS
ALTERNATE 1 – HIGH IMPACT
Approximately 1,940 LF of Water Line
Approximately 2,130 LF of Wastewater Line
Approximately 8,135 LF of Gas Line
Approximately 900 LF of Overhead Electric Line
Approximately 720 LF of Telephone / Fiber Optic Line
ALTERNATE 2 & 2A – MODERATE IMPACT
Approximately 1,940 LF of Water Line
Approximately 2,130 LF of Wastewater Line
Approximately 8,135 LF of Gas Line
Approximately 900 LF of Overhead Electric Line
Approximately 720 LF of Telephone / Fiber Optic Line
ALTERNATE 3 – LOW IMPACT
Approximately 840 LF of Water Line
Approximately 2,130 LF of Wastewater Line
Approximately 640 LF of Gas Line
Approximately 900 LF of Overhead Electric Line
Approximately 240 LF of Telephone / Fiber Optic Line

## Slide 21
03
Budget and Cost Estimate Update

## Slide 22: PROJECT COST ESTIMATE UPDATE

## Slide 23
04
Schedule of Activities

## Slide 24: SCHEDULE OF ACTIVITIES
Final Schematic – Dec 2014
Final Plans – Sept 2015
Let for Construction – Dec 2015
Begin Construction – Feb 2016
ROW Acquisition. Fewer parcels will reduce time requirement. Schedule will need to be extended about 4 months if ROW services not performed through a supplement to the base contract.
ROW Acquisition – Jan 2016

## Slide 25
QUESTIONS?